## Sprint i
ID | User Story | Task ID | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Assigned | Names and Contribution Percentage
1 | Create documentation | 1 | Create kanban board | 1 | Establish documentation, address feedback, establish requirements, begin implementation, and create ui mockup | DOC | 1 | 1 | Brianna | Brianna 100%
|  | 1.1 | Create product backlog |  |  | DOC | 1 | 1 | Brianna | Brianna 100%
|  | 1.2 | Create SRS document |  |  | DOC | 1 | 1 | Brianna | Brianna 100%
|  | 1.3 | Create sprint backlog |  |  | DOC | 1 | 1 | Sarah | Sarah 100%
|  | 1.4 | Put user stories in sprint backlog |  |  | DOC | 1 | 1 | Sarah | Sarah 100%
|  | 1.5 | Put user stories in product backlog |  |  | DOC | 1 | 1 | Brianna | Brianna 100%
2 | Address feedback | 2 | Address and respond to feedback in product description doc |  |  | DOC | 1 | 1 | Roisin | Roisin 100%
|  | 2.1 | Address and respond to feedback in user story doc |  |  | DOC | 1 | 1 | Emily | Emily 100%
3 | Establish functional and nonfunctional requirements | 3 | Write nonfunctional requirements |  |  | DOC | 2 | 2 | All but Dean | Brianna 20%, Roisin 20%, Emily 40%, Sarah 20%
|  | 3.1 | Write functional requirements |  |  | DOC | 2 | 2 | All but Emily | Brianna 20%, Roisin 20%, Dean 40%, Sarah 20%
4 | Begin impelemtation | 4 | Create actual implementation |  |  | GH | 2 | 2 | Brianna | Brianna 100%
|  | 4.1 | Update ReadMe file with download instructions |  |  | GH | 1 | 1 | Brianna | Brianna 100%
|  | 4.2 | Make current links document |  |  | GH | 1 | 1 | Brianna | Brianna 100%
5 | UI mockup | 5 | UI mockup |  |  | UI | 3 | 3 | Roisin | Roisin 100%
6 | Quality checking | 6 | Quality check sprint backlog |  |  | QC | 1 | 1 | Brianna | Brianna 100%
|  | 6.1 | Quality check product backlog |  |  | QC | 1 | 1 | Sarah | Sarah 100%
|  | 6.2 | Quality check user story feedback |  |  | QC | 1 | 1 | Roisin | Roisin 100%
|  | 6.3 | Quality check functional requirements |  |  | QC | 1 | 1 | Emily | Emily 100%
|  | 6.4 | Quality check feedback in product description |  |  | QC | 1 | 1 | Dean | Dean 100%
|  | 6.5 | Quality check nonfunctional requirements |  |  | QC | 1 | 1 | Dean | Dean 100%

## Column Description
o Sprint Goal and Number. o Story copied from the project backlog or a sprint task story. o Story Type: F (functional), NF (non-functional) with a subtype: B (bug), T (technical work), KA(knowledge acquisition, technical or design/users). o Story Points. o Story Points Completed. o Team Member Names and percentage of contribution to the story.
Note there is another option this year to export this document instead from Github projects, see https://discord.com/channels/1280324227790278737/1280324228255711263/1291882302460399657