## Sheet1
ID | User Story | Sprint Number | Story Priority | Story Status | Story Points
Artifact 1 | Create documentation | 1 | High | Done | 6
Artifact 2 | Addressing Feedback | 1 | High | Done | 2
Artifact 3 | Establish Functional and Nonfunctional Requirements | 1 | High | Done | 4
Artifact 4 | Begin Implementation | 1 | High | Done | 2
Artifact 5 | Create UI Mockup | 1 | High | Done | 2
Artifact 6 | Quality Checking so User Stories can be Implemented | 1 | High | Done | 6
1 | As a user, I want to receive gentle and encouraging feedback when I don’t complete a task so that I stay motivated and don’t feel discouraged by negative or harsh responses. | 4 | High | To-Do | 2
2 | As a user, I want the application to recognize when I’m developing positive habits and maintaining consistency so that I can be rewarded for my progress and stay motivated. | 4 | High | To-Do | 3
3 | As a user, I want the user interface of the application to be readable, easy to understand, and uses inviting language so that I am not distracted from my progress by frustration from navigating a difficult or harsh interface. | 3 | High | In Progress | 6
4 | As a user, I want to be rewarded for completing tasks without needing reminders so that I am encouraged to keep healthier habits. | 4 | High | To-Do | 2
5 | As a user, I want weekly encouraging feedback on how well I did for the week so that I know how many tasks I finished or missed and which tasks I would like to carry over if they were missed. | 5 | High | To-Do | 2
6 | As a user, I want the application to feel fun, friendly and inviting, so that using the application feels rewarding and helps to build self-confidence. | 3 | High | In Progress | 1
7 | As a user, I want to feel attached to my avatar and help it grow so that it encourages me to take better care of myself. | 4 | High | To-Do | 2
8 | As a user, I want my avatar to actively encourage me to do my tasks so that I feel more confident in completing what I set out for myself. | 4 | High | To-Do | 2
9 | As a college student, I want a timer feature that tracks my study sessions and rewards me for staying focused so that I feel motivated to maintain productive study habits. | 5 | Low | To-Do | 1
10 | As a user, I want a healthy eating feature that is customizable to my personal dietary needs so that I can track what’s in my meals. | 5 | Low | To-Do | 2
11 | As a user, I want to track my goals depending on my location/GPS so I can hold myself accountable for going to the area. | 5 | Low | To-Do | 5
12 | As a user, I want to efficiently organize my tasks by category and topic to keep track of my due dates. | 5 | Low | To-Do | 2
13 | As a user, I want a feature that allows the user to track the amount of sleep and which hours they are sleeping each night so that I can build a healthy sleep schedule. | 4 | Medium | To-Do | 2
14 | As a user, I want to be able to set a schedule/routine for friendly and supportive reminders so that I don’t forget to do basic tasks like making/eating lunch. | 4 | Medium | To-Do | 2
15 | As a user, I want to know if my stored data is secure so I can feel confident in sharing/storing personal information. | 5 | Medium | To-Do | 4
16 | As a user, I want to have AI suggest tasks automatically based on previous tasks to save time setting up tasks. | 5 | Medium | To-Do | 3
17 | As a user, I want to automatically renew tasks, by selecting a daily/weekly option when the task is created so that repeat tasks are easy to set up and use. | 4 | Medium | To-Do | 3

## Description of Columns
ID: unique # for each story * Story: Contains the user stories (one story per row) in priority order ▪ Formatted as “As a <user role>, I need to <feature needed> because of <benefit>. o Sprint: The story’s sprint number (when it gets implemented) o Priority: H (high), M (medium), L (low) o Status: Backlog, To Do, IP (in progress), QC (quality checking), D (done) o Estimate / Story Points: Number of story points gives an indication of the difficulty of the story’s development and testing as well as possibly an estimate of the number of hours to design, implement, and test the story.
The basic idea of story points is a story with 3 points is 3x the effort as a 1 point story, 2 points is 2x the effort, etc. In general without much experience it's hard for you to estimate relative feature sizes. Just do your best. Here's more information https://www.mountaingoatsoftware.com/blog/what-are-story-points
Note there is another option this year to export this document instead from Github projects, see https://discord.com/channels/1280324227790278737/1280324228255711263/1291882302460399657