## Sprint i
ID | User Story | Task ID | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Assigned | Names and Contribution Percentage
Artifact 1 | Create documentation | 1 | Create kanban board | 1 | Establish documentation, address feedback, establish requirements, begin implementation, and create ui mockup | DOC | 1 | 1 | Brianna | Brianna 100%
|  | 1.1 | Create product backlog |  |  | DOC | 1 | 1 | Brianna | Brianna 100%
|  | 1.2 | Create SRS document |  |  | DOC | 1 | 1 | Brianna | Brianna 100%
|  | 1.3 | Create sprint backlog |  |  | DOC | 1 | 1 | Sarah | Sarah 100%
|  | 1.4 | Put user stories in sprint backlog |  |  | DOC | 1 | 1 | Sarah | Sarah 100%
|  | 1.5 | Put user stories in product backlog |  |  | DOC | 1 | 1 | Brianna | Brianna 100%
Artifact 2 | Address feedback | 2 | Address and respond to feedback in product description doc |  |  | DOC | 1 | 1 | Roisin | Roisin 100%
|  | 2.1 | Address and respond to feedback in user story doc |  |  | DOC | 1 | 1 | Emily | Emily 100%
Artifact 3 | Establish functional and nonfunctional requirements | 3 | Write nonfunctional requirements |  |  | DOC | 2 | 2 | All but Dean | Brianna 20%, Roisin 20%, Emily 40%, Sarah 20%
|  | 3.1 | Write functional requirements |  |  | DOC | 2 | 2 | All but Emily | Brianna 20%, Roisin 20%, Dean 40%, Sarah 20%
Artifact 4 | Begin impelemtation | 4 | Create actual implementation |  |  | GH | 2 | 2 | Brianna | Brianna 100%
|  | 4.1 | Update ReadMe file with download instructions |  |  | GH | 1 | 1 | Brianna | Brianna 100%
|  | 4.2 | Make current links document |  |  | GH | 1 | 1 | Brianna | Brianna 100%
Artifact 5 | UI mockup | 5 | UI mockup |  |  | UI | 3 | 3 | Roisin | Roisin 100%
Artifact 6 | Quality checking | 6 | Quality check sprint backlog |  |  | QC | 1 | 1 | Brianna | Brianna 100%
|  | 6.1 | Quality check product backlog |  |  | QC | 1 | 1 | Sarah | Sarah 100%
|  | 6.2 | Quality check user story feedback |  |  | QC | 1 | 1 | Roisin | Roisin 100%
|  | 6.3 | Quality check functional requirements |  |  | QC | 1 | 1 | Emily | Emily 100%
|  | 6.4 | Quality check feedback in product description |  |  | QC | 1 | 1 | Dean | Dean 100%
|  | 6.5 | Quality check nonfunctional requirements |  |  | QC | 1 | 1 | Dean | Dean 100%
Artifact 7 | Upkeep Documentation | 7 | Handle necessary upkeep/updates on product backlog | 2 | Upkeep documentation, improve UI mockups, begin implementation, and quality check work | DOC | 1 | 1 | Brianna | Brianna 100%
|  | 7.1 | Make architecture design doc |  |  | DOC | 1 | 1 | Emily | Emily 100%
|  | 7.2 | Fill in SRS document section 1 and 2 |  |  | DOC | 1 | 1 | Emily, Dean | Emily 50%, Dean 50%
|  | 7.3 | Handle necessary upkeep/updates on sprint backlog |  |  | DOC | 1 | 1 | Sarah | Sarah 100%
|  | 7.4 | Make use case diagrams |  |  | DOC | 2 | 2 | Brianna, Sarah | Brianna 66%, Sarah 34%
|  | 7.5 | Make use case descriptions |  |  | DOC | 2 | 2 | Brianna, Sarah | Brianna 66%, Sarah 34%
|  | 7.6 | Add quality checking policy to wiki |  |  | GH | 1 | 1 | Brianna | Brianna 100%
|  | 7.7 | Improve requirements in the SRS doc |  |  | DOC | 1 | 1 | Dean, Brianna | Dean 50%, Brianna 50%
Artifact 8 | UI Mockups | 8 | Address feedback specific to ui mockups |  |  | UI | 1 | 1 | Roisin | Roisin 100%
|  | 8.1 | Make improvements on UI mockups |  |  | UI | 1 | 1 | Roisin | Roisin 100%
|  | 8.2 | Sleep Tracker Mockup |  |  | UI | 1 | 1 | Roisin | Roisin 100%
User Story 3 | As a user, I want the user interface of the application to be readable, easy to understand, and uses inviting language so that I am not distracted from my progress by frustration from navigating a difficult or harsh interface. | 3 | Implement Homepage |  |  | IM | 3 | 3 | Emily, Sarah, Brianna | Emily 33%, Sarah 33%, Brianna 33%
|  | 3.1 | React's routing features |  |  | IM | 3 | 3 | Emily, Brianna | Emily 50%, Brianna 50%
Artifact 9 | Quality checking | 9 | Quality check sprint backlog |  |  | QC | 1 | 1 | Brianna | Brianna 100%
|  | 9.1 | Quality check product backlog |  |  | QC | 1 | 1 | Sarah | Sarah 100%
|  | 9.2 | Quality check use case diagrams |  |  | QC | 1 | 1 | Brianna, Sarah | Brianna 50%, Sarah 50%
|  | 9.3 | Quality check use case descriptions |  |  | QC | 1 | 1 | Brianna, Sarah | Brianna 50%, Sarah 50%
|  | 9.4 | Quality check Architecture Design Doc |  |  | QC | 1 | 1 | Brianna | Brianna 100%
|  | 9.5 | Quality check SRS document section 1 and 2 |  |  | QC | 1 | 1 | Emily, Dean | Emily 50%, Dean 50%
Artifact 10 | Upkeep Documentation | 10 | Maintain sprint backlog | 3 | Upkeep documentation, improve UI mockups, make progress on navigation, display, and back end, and quality check work | DOC | 1 | 1 | Sarah | Sarah 100%
|  | 10.1 | Maintain product backlog |  |  | DOC | 1 | 1 | Brianna | Brianna 100%
|  | 10.2 | Domain Model |  |  | DOC | 2 | 2 | Emily | Emily 100%
|  | 10.3 | Fill in rest of SRS document section 3 |  |  | DOC | 1 | 1 | Roisin | Roisin 100%
|  | 10.4 | Fill in SRS document section 6 |  |  | DOC | 1 | 1 | Dean | Dean 100%
|  | 10.5 | Fill in parts of SRS document section 4 |  |  | DOC | 1 | 1 | Dean | Dean 50%, Brianna 50%
|  | 10.6 | Update Architecture Design document if necessary |  |  | DOC | 1 | 1 | Emily | Emily 100%
Artifact 11 | Address feedback | 11 | Address feedback on and maintain Use Case Descriptions and Diagrams |  |  | DOC | 1 | 1 | Brianna | Brianna 100%
|  | 11.1 | Address feedback on Architecture Design document |  |  | DOC | 1 | 1 | Emily | Emily 100%
Artifact 12 | UI | 12 | Update UI mockups based on Usability Testing |  |  | UI | 1 | 1 | Roisin | Roisin 100%
User Story 3/ User Story 6 | As a user, I want the user interface of the application to be readable, easy to understand, and uses inviting language so that I am not distracted from my progress by frustration from navigating a difficult or harsh interface. As a user, I want the application to feel fun, friendly and inviting, so that using the application feels rewarding and helps to build self-confidence. | 3.0/6.0 | Implement navigation functionality |  |  | IM | 2 | 2 | Emily, Sarah, Dean | Emily 50%, Sarah 50%
|  | 3.1/6.1 | Implement Registration page (firebase) |  |  | IM | 3 | 3 | Emily | Emily 100%
|  | 3.2/6.2 | Implement Homepage/Avatarpage |  |  | IM | 3 | 3 | Sarah | Sarah 100%
|  | 3.3/6.3 | Begin task implementation |  |  | IM | 3 | 3 | Emily, Sarah, Dean | Sarah 100%
Artifact 13 | Implementation (not user story specific) | 13 | Record implementation video |  |  | DOC | 2 | 2 | Sarah | Sarah 100%
|  | 13.1 | Continuous Integration |  |  | IM | 2 | 2 | Brianna | Brianna 100%
Artifact 14 | Quality Checking | 14 | Quality check sprint backlog |  |  | QC | 1 | 1 | Brianna | Brianna 100%
|  | 14.1 | Quality check product backlog |  |  | QC | 1 | 1 | Sarah | Sarah 100%
|  | 14.2 | Quality check section 3 of SRS document |  |  | QC | 1 | 1 | Brianna | Brianna 100%
|  | 14.3 | Quality check section 4 of SRS document |  |  | QC | 1 | 1 | Brianna | Brianna 100%
|  | 14.4 | Quality check new/updated ui mockups |  |  | QC | 1 | 1 | Brianna | Brianna 100%
|  | 14.5 | Quality check section 6 of SRS document |  |  | QC | 1 | 1 | Roisin | Roisin 100%
|  | 14.6 | Quality check domain model |  |  | QC | 1 | 1 | Dean | Brianna 100%
|  | 14.7 | Quality check use case diagram feedback |  |  | QC | 1 | 1 | Emily | Emily 100%
Artifact 15 | Upkeep Documentation and UI Mockups | 15 | Maintain product backlog | 4 | Upkeep documentation, improve UI mockups, make progress on task functionality, avatar display, organization, and back end, and quality check work | DOC | 1 | 1 | Brianna | Brianna 100%
|  | 15.1 | Maintain sprint backlog |  |  | DOC | 1 | 1 | Sarah | Sarah 100%
|  | 15.2 | Fill in the tables at the bottom of assignment descriptor |  |  | DOC | 1 | 1 | Emily | Emily 100%
|  | 15.3 | Handle Round 2 of Usability Testing (3 people) |  |  | DOC | 2 | 2 | Dean | Dean 70%, Brianna 30%
|  | 15.4 | Update UI mockups if necessary from usability testing |  |  | UI | 1 | 1 | Roisin | Roisin 100%
Artifact 16 | Design patterns and models | 16 | Make design pattern in technical design document |  |  | DOC | 1 | 1 | Roisin | Roisin 100%
|  | 16.1 | Handle technical design pattern in domain model doc |  |  | DOC | 1 | 1 | Roisin | Roisin 100%
|  | 16.2 | Detailed design model for registration page in domain model doc |  |  | DOC | 1 | 1 | Emily | Emily 100%
|  | 16.3 | Detailed design model for sign-in page in domain model doc |  |  | DOC | 1 | 1 | Dean | Dean 100%
|  | 16.4 | Detailed design model for avatar page in domain model doc |  |  | DOC | 1 | 1 | Brianna | Brianna 100%
|  | 16.5 | Detailed design model for tasks page in domain model doc |  |  | DOC | 1 | 1 | Roisin | Roisin 100%
Artifact 17 | Address Feedback | 17 | Get feedback from Dr. Greg on usability testing script |  |  | DOC | 1 | 1 | Dean | Dean 100%
|  | 17.1 | Respond to feedback on Domain Model |  |  | DOC | 1 | 1 | Emily | Emily 100%
|  | 17.2 | Address feedback from Dr. Greg |  |  | DOC | 1 | 1 | Brianna | Brianna 100%
Artifact 18 | Quality Checking | 18 | Quality check sprint backlog |  |  | QC | 1 | 1 | Brianna | Brianna 100%
|  | 18.1 | Quality check usability testing report |  |  | QC | 1 | 1 | Brianna | Brianna 100%
|  | 18.2 | Quality check technical design in domain model document |  |  | QC | 1 | 1 | Roisin | Roisin 100%
|  | 18.3 | Quality check design pattern in domain model doc |  |  | QC | 1 | 1 | Roisin | Roisin 100%
|  | 18.4 | Quality check updated UI mockups if necessary |  |  | QC | 1 | 1 | Dean | Dean 100%
|  | 18.5 | Quality check product backlog |  |  | QC | 1 | 1 | Sarah | Sarah 100%
User Story 7 | As a user, I want to feel attached to my avatar and help it grow so that it encourages me to take better care of myself. | 7 | Avatar Page implementation |  |  | IM | 3 | 3 | Brianna | Brianna 100%
|  | 7.1 | Create Avatar options |  |  | IM | 2 | 2 | Sarah | Sarah 100%
User Story 15 | As a user, I want to know if my stored data is secure so I can feel confident in sharing/storing personal information. | 15 | Implement Firebase for backend |  |  | IM | 3 | 3 | Emily, Dean, Roisin | Emily 33%, Dean 33%, Roisin 33%
|  | 15.1 | Implement Sign up/Log in classes |  |  | IM | 3 | 3 | Emily, Dean, Roisin | Emily 33%, Dean 33%, Roisin 33%
User Story 12/ User Story 17 | As a user, I want to efficiently organize my tasks by category and topic to keep track of my due dates. As a user, I want to automatically renew tasks, by selecting a daily/weekly option when the task is created so that repeat tasks are easy to set up and use. | 12.0/17.0 | Modify the pages meant to display tasks |  |  | IM | 2 | 2 | Sarah | Sarah 100%
|  | 12.1/17.1 | Implement Add Task CSS |  |  | IM | 3 | 3 | Roisin | Roisin 100%
|  | 12.2/17.2 | Implement Add Task functionality to task page |  |  | IM | 3 | 3 | Emily | Emily 100%
|  | 12.3/17.3 | Organize current code |  |  | IM | 3 | 3 | Dean | Dean 100%

## Column Description
o Sprint Goal and Number. o Story copied from the project backlog or a sprint task story. o Story Type: F (functional), NF (non-functional) with a subtype: B (bug), T (technical work), KA(knowledge acquisition, technical or design/users). o Story Points. o Story Points Completed. o Team Member Names and percentage of contribution to the story.
Note there is another option this year to export this document instead from Github projects, see https://discord.com/channels/1280324227790278737/1280324228255711263/1291882302460399657